ORCA Project Planning

Conversation Record & 6-Day Prototype Build Plan

Marine EcOsystem Reasoning with Collaborative Agents — SIH26176 (ISRO)

# Project Analysis & Build Plan

Reviewed the SRS, HLD, and LLD together. The design is already well-decomposed into independent modules (4 specialist agents + Planner/Synthesis + Bhashini layer + client + data layer), which maps cleanly onto a 6-person team. Below is the domain breakdown, role assignment, tech stack, and a day-by-day schedule compressed from the original 9-day plan into 6 days.

## 1. Domain Fields Required

| Domain | Where it's used |
| --- | --- |
| Backend / API engineering | FastAPI Gateway, session/WebSocket management |
| Agentic AI / LLM orchestration | Planner Agent, Synthesis Agent, LangGraph state graph |
| Prompt engineering / NLP | Entity extraction, citation-constrained response generation |
| Geospatial engineering (GIS) | Geofencing Agent (PostGIS, Shapely, point-in-polygon, haversine) |
| API integration / data engineering | Weather Agent, Ocean Agent, Data Access adapters (INCOIS, weather provider, GIS boundary data) |
| Rules-based systems design | Risk/Safety Agent decision tree (deterministic, not ML) |
| Multilingual speech tech | Bhashini integration (ASR/TTS/Lang-ID) |
| Frontend / web development | React client, chat UI, voice capture/playback |
| Mapping / visualization | Leaflet map panel, marker/zone rendering, agent-trace viewer |
| Database engineering | PostgreSQL + PostGIS schema, session/turn/invocation tables |
| DevOps | Containerization, single-app deployment, env-secret management |
| QA / integration testing | Cross-agent integration tests, safety-verdict fixture testing |

Note: no real ML model training is needed — the Planner routing and Risk verdict are both explicitly deterministic decision trees per the LLD, and the only “AI” is LLM API calls (entity extraction, response synthesis). This significantly de-risks the build.

## 2. Role Assignments (6 Members)

Each person owns a vertically complete slice (their own agent/module end-to-end) so nobody blocks anybody else after Day 1.

| # | Role | Owns (LLD refs) | Tech Stack | Tools |
| --- | --- | --- | --- | --- |
| P1 | Backend/Orchestration Lead | FastAPI Gateway, Planner Agent, session lifecycle, LangGraph wiring | Python, FastAPI, LangGraph, WebSockets, Pydantic | GitHub, Postman/Insomnia, Docker |
| P2 | LLM/Synthesis Engineer | Synthesis Agent, LLM entity-extraction prompts, citation-coverage check | Python, Claude/GPT API (function-calling), Pydantic | Anthropic/OpenAI console, GitHub |
| P3 | Weather & Ocean Data Engineer | Weather Agent, Ocean Agent, WeatherDataAdapter, INCOISAdapter | Python, httpx/requests, haversine calc | Postman, GitHub, sample API docs |
| P4 | Geospatial & Risk Engineer | Geofencing Agent, Risk/Safety Agent, DB schema, GISBoundaryAdapter | Python, Shapely, PostGIS, PostgreSQL | pgAdmin/DBeaver, QGIS, GitHub |
| P5 | Frontend Engineer (Core UI) | React chat interface, voice I/O, Bhashini client integration, multi-turn history | React, WebSocket client, Web Audio API | VS Code, Figma (optional), GitHub |
| P6 | Frontend Engineer (Map/Trace) + QA/Integration Lead | Leaflet map panel, agent-trace viewer, geofence boundary rendering, E2E testing, deployment, demo script | React, Leaflet, Docker Compose | GitHub Actions, Docker, browser devtools |

## 3. Six-Day Schedule

Compressing SRS Section 6.5's 9-day plan into 6 days means Sprint 0 and Sprint 1 partially merge, and language coverage is capped at 2 languages (not expanded) to protect integration time.

| Day | P1 | P2 | P3 | P4 | P5 | P6 |
| --- | --- | --- | --- | --- | --- | --- |
| Day 1 | Repo scaffold, FastAPI skeleton, agent interface contracts | Confirm LLM API access, draft entity-extraction prompt | Confirm INCOIS + weather API access, sample calls | Confirm/download IMBL+MPA GIS data, set up PostgreSQL+PostGIS | React scaffold, basic chat layout | Leaflet setup, Docker skeleton |
| Day 2 | Planner decision-tree (Fig.1) skeleton | Synthesis Agent skeleton + citation format | Weather Agent + adapter (returns structured data) | DB schema (session/turn/invocation/boundary) migration | Text-mode chat working E2E (mock backend) | Map renders static markers |
| Day 3 | Planner entity extraction wired to P2's LLM calls | Synthesis composes from mock agent outputs | Ocean Agent + haversine nearest-PFZ | Geofencing Agent (point-in-polygon + IMBL buffer) | Voice capture UI (mic → base64) | Agent-trace panel (static → live later) |
| Day 4 | Full Planner→4 Agents routing wired, WebSocket streaming | Bhashini TTS/ASR wrapper (2 languages), Synthesis multilingual | Weather+Ocean returning live data to Planner | Risk/Safety Agent verdict tree (Fig.2), unit-tested against fixtures | Wire real WebSocket to backend, display streamed trace | Real-time map markers + geofence zone overlay |
| Day 5 | Full integration: E2E query → 4 agents → Risk → Synthesis | Citation-coverage check, response regeneration on failure | Adapter fallback/error states (status='unavailable') | Verify UNSAFE/INSUFFICIENT_DATA never overridden (safety tests) | Multi-turn conversation history UI | Bug bash across full flow, error-state UI |
| Day 6 | Freeze + fix; deploy single containerized app | Final prompt tuning, demo query rehearsal | Final adapter reliability check | Final DB/geofence sanity check | UI polish, accessibility text labels | Full demo rehearsal, deployment verification, fallback script |

Effort Estimate Per Module (for tracking)

| Module | Owner | Est. effort |
| --- | --- | --- |
| FastAPI Gateway + session mgmt | P1 | 1 day |
| Planner Agent (routing + context) | P1 | 1.5 days |
| Synthesis Agent + citation check | P2 | 1.5 days |
| Bhashini integration (2 languages) | P2 | 1.5 days |
| Weather Agent + adapter | P3 | 1 day |
| Ocean Agent + adapter | P3 | 1 day |
| Geofencing Agent | P4 | 1 day |
| Risk/Safety Agent (decision tree) | P4 | 1 day |
| DB schema + PostGIS setup | P4 | 0.5 day |
| React chat UI (text + voice) | P5 | 2 days |
| Multi-turn history | P5 | 0.5 day |
| Leaflet map + geofence overlay | P6 | 1.5 days |
| Agent-trace viewer | P6 | 1 day |
| Integration testing + deployment | P6 (+ all Day 6) | 1.5 days |

Scope Notes

- Bhashini scoped to 2 languages only (not the “full supported set” the SRS lists as Must Have).

- FR-ALERT-1 (proactive alerting) treated as dropped — it is marked Could-have and already excluded from Sprint 4's exit criteria even at 9 days.

- The SRS explicitly calls a 9-day window “still compressed” for four agents plus full multilingual support — 6 days requires trimming scope, not just compressing the schedule.

## 4. Parallelization of Work

The work is largely parallel, provided the LLD's strict data contracts (WeatherResult, PFZResult, GeofenceResult, RiskVerdict) are locked before implementation begins. No agent calls another directly — each is only invoked by the Planner and reports to Synthesis/Risk — and each has its own external data source, so members never touch the same code. The frontend can build against mocked WebSocket messages (schemas already defined in LLD §5.2) without a working backend at all.

Full independence has limits: the Risk/Safety Agent and Synthesis Agent are the points where all other agents' outputs converge, so they can be built against fixtures early but only truly validated once the real agents exist. Bhashini and the voice UI also have a two-way dependency since real audio behavior is harder to mock than JSON.

Recommended approach: Day 1 for a contract-lock sync so every team member codes against the same schemas, Days 2–4 for true parallel builds against mocks/fixtures, Day 5 reserved fully for integration (swapping mocks for real calls, where mismatches surface), and Day 6 for hardening and demo rehearsal only — no new integration work. The main risk is silent contract drift rather than an inability to parallelize, so a daily schema-conformance check by the integration lead (P1 or P6) is worth the small overhead.